## Dashboard
OSSPolicyGuard — Requirements Tracker
Product | OSSPolicyGuard v0.1.0
Product Leads | Surya Nalluri · Aluri
Last Updated | August 2026
PROGRESS OVERVIEW
Metric | Count | % Total
Total Requirements
Done
In Progress
Not Started
Blocked
% Complete
PRIORITY BREAKDOWN
P0 (Critical)
P1 (High)
P2 (Future)
WORKSTREAM SUMMARY
Workstream | Total | Done | In Progress | Not Started | Blocked
WS 1: Architecture & Foundation
WS 2: Identity & Dependency Ingestion
WS 3: Evidence Providers & Data Quality
WS 4: Vulnerability & Exploitability
WS 5: Supply Chain & Malicious Package Defense
WS 6: Policy Engine & Explainability
WS 7: Outputs APIs & Developer Integrations
WS 8: Enterprise Governance & Exceptions
WS 9: Security Privacy & Reliability
WS 10: Quality Release & Documentation
WS 11: Adoption Validation & Evidence
WS 12: Differentiation Research & IP Controls
WS 13: License Compliance
WS 14: Dependency Management Extended
WS 15: Evidence Providers Extended
WS 16: Supply Chain Defense Extended
WS 17: Policy Engine Extended
WS 18: Outputs & Integrations Extended
WS 19: Quality & Compliance Extended
WS 20: Research Extended

## Requirements
OPG ID | WS# | Feature Name | Workstream | Description / Acceptance Criteria | Priority | Status | Implementation Notes | Module / File | Linked OPG IDs
OPG-001 | 1 | Public product contract | Architecture & Foundation | README identifies target users, supported ecosystems, decision semantics, limitations, and five-minute quick start | P0 | In Progress | README.md updated with product contract | README.md
OPG-002 | 1 | Safe technical-signal policy | Architecture & Foundation | Default score unchanged when maintainer identity/location changes; jurisdiction rules are opt-in and excluded from maliciousness inference | P0 | Done | Safe-signal policy enforced in scoring logic | oss_scorer.py
OPG-003 | 1 | Modular package architecture | Architecture & Foundation | Move monolithic scorer into typed models, providers, policy, reports, manifest modules; CLI behavior and golden outputs remain compatible | P0 | In Progress | Module skeleton created in src/osspolicyguard/ | src/osspolicyguard/ | OPG-005
OPG-004 | 1 | Installable Python package | Architecture & Foundation | Clean Python 3.11/3.12 environment installs wheel and runs osspolicyguard --version and one offline fixture scan | P0 | Done | pyproject.toml + src layout configured | pyproject.toml
OPG-005 | 1 | Stable public Python API | Architecture & Foundation | Expose documented scan_package, scan_manifest, evaluate_policy APIs with typed inputs/results and semver compatibility tests | P1 | In Progress | scan_package() implemented; scan_manifest() stub | src/osspolicyguard/cli.py | OPG-003
OPG-006 | 1 | Domain exception hierarchy | Architecture & Foundation | Define config, provider, identity, policy, report, and internal error types; CLI maps each to a message and exit code without traceback | P0 | Done | Full exception hierarchy implemented | src/osspolicyguard/exceptions.py
OPG-007 | 1 | Dependency injection | Architecture & Foundation | Providers, clock, cache, and policy store can be injected; unit tests run without patching global requests or live network calls | P0 | In Progress | ProviderBase ABC and NullProvider implemented | src/osspolicyguard/providers/__init__.py | OPG-023
OPG-008 | 1 | Configuration layering | Architecture & Foundation | Merge defaults, org policy, repo policy, env vars, and CLI overrides in documented precedence; config explain shows winning source | P0 | In Progress | Env var overrides + YAML defaults implemented | oss_scorer.py / config.yaml
OPG-009 | 1 | Configuration schema and migration | Architecture & Foundation | Versioned JSON Schema for YAML config; invalid keys fail with path-specific messages; older versions migrate deterministically | P0 | Done | config.schema.json (JSON Schema draft 2020-12) | config.schema.json
OPG-010 | 1 | Structured logging | Architecture & Foundation | Emit JSON or human logs with request ID, package coords, provider, latency, retry count, outcome; tokens redacted in tests | P1 | Done | RedactingFilter + StructuredFormatter implemented | src/osspolicyguard/logging_config.py
OPG-011 | 1 | Feature flag framework | Architecture & Foundation | Experimental providers disabled by default, named, auditable, covered by tests for enabled/disabled behavior | P1 | Not Started |  | TBD
OPG-012 | 2 | Canonical Package URL identity | Identity & Dependency Ingestion | Normalize every input to validated purl; equivalent spellings produce one canonical identifier | P0 | Done | PackageUrl dataclass with per-ecosystem normalization | src/osspolicyguard/identity.py
OPG-013 | 2 | Repository resolution with confidence | Identity & Dependency Ingestion | Resolve package-to-repository links; report source, confidence, redirects, and ambiguity | P0 | In Progress | GitHub URL parsing and resolution in place | oss_scorer.py | OPG-026
OPG-014 | 2 | Exact version resolution | Identity & Dependency Ingestion | Resolve analyzed version and immutable artifact digest; reject ranges when deterministic resolution required | P0 | Not Started |  | TBD | OPG-012
OPG-015 | 2 | PyPI requirements ingestion | Identity & Dependency Ingestion | Parse requirements.txt including pins, extras, markers, hashes, includes, constraints, editable/VCS entries | P0 | In Progress | Basic requirements.txt scanning in CI action | scripts/ | OPG-012
OPG-016 | 2 | Python lockfile ingestion | Identity & Dependency Ingestion | Parse Poetry, Pipenv, uv, PEP 665-compatible lock data; retain direct/transitive relationship | P1 | Not Started |  | TBD | OPG-015
OPG-017 | 2 | npm manifest ingestion | Identity & Dependency Ingestion | Parse package.json dependency sections and workspace definitions without executing scripts; normalize scoped packages | P0 | In Progress | Basic package.json scanning in CI action | scripts/ | OPG-012
OPG-018 | 2 | npm lockfile ingestion | Identity & Dependency Ingestion | Support package-lock v2/v3, npm-shrinkwrap, yarn.lock, pnpm-lock; preserve resolved URL, integrity hash, depth | P0 | Not Started |  | TBD | OPG-017
OPG-019 | 2 | SBOM ingestion | Identity & Dependency Ingestion | Accept CycloneDX 1.5+ and SPDX 2.3 JSON; validate schema and translate components to internal graph | P1 | Not Started |  | TBD | OPG-020
OPG-020 | 2 | Dependency graph construction | Identity & Dependency Ingestion | Build deterministic directed graph with roots, direct/transitive depth, cycles, duplicates, and unresolved nodes | P0 | Not Started |  | TBD | OPG-012
OPG-021 | 2 | Changed-dependency detection | Identity & Dependency Ingestion | Given base and head manifests/locks, identify added, removed, upgraded, downgraded, source-changed components | P0 | Not Started |  | TBD | OPG-020
OPG-022 | 2 | Monorepo discovery | Identity & Dependency Ingestion | Discover supported manifests within configurable paths, honor ignore rules, prevent traversal outside workspace | P1 | Not Started |  | TBD | OPG-015,OPG-017
OPG-023 | 3 | Provider interface contract | Evidence Providers & Data Quality | Every provider returns typed status, evidence, retrieval timestamp, source URL, freshness, confidence, normalized errors | P0 | In Progress | ProviderBase + ProviderResponse contract implemented | src/osspolicyguard/providers/__init__.py | OPG-007
OPG-024 | 3 | HTTP client resilience | Evidence Providers & Data Quality | Central client enforces connect/read timeouts, bounded retries with jitter, Retry-After, rate limits, user agent, max response size | P0 | In Progress | Retry/backoff in ProviderBase | src/osspolicyguard/providers/__init__.py | OPG-023
OPG-025 | 3 | Persistent evidence cache | Evidence Providers & Data Quality | Cache provider responses by normalized request and policy-relevant headers; TTL, offline mode, corruption recovery tested | P0 | Not Started |  | TBD | OPG-023
OPG-026 | 3 | GitHub metadata provider | Evidence Providers & Data Quality | Collect repo state, activity, releases, contributors, security policy, archival status, branch protection using least-privilege auth | P0 | In Progress | GitHubProvider implemented with caching | oss_scorer.py | OPG-023
OPG-027 | 3 | OpenSSF Scorecard provider | Evidence Providers & Data Quality | Ingest overall and individual checks, source commit, evaluation date, unavailable status; never substitute zero for missing data | P0 | In Progress | ScorecardProvider with enabled flag | oss_scorer.py | OPG-023
OPG-028 | 3 | OSV provider | Evidence Providers & Data Quality | Query exact ecosystem/name/version; deduplicate aliases; retain advisory ranges, fixed versions, references, modified time | P0 | In Progress | check_osv() with MAL-/GHSA classification | oss_scorer.py | OPG-040
OPG-029 | 3 | NVD provider | Evidence Providers & Data Quality | Retrieve CVE, CVSS versions, CWE, CPE match rationale, publication/modification times, and rejected status | P1 | In Progress | NVD v2 API integration with EPSS enrichment | oss_scorer.py | OPG-030
OPG-030 | 3 | EPSS provider | Evidence Providers & Data Quality | Retrieve probability, percentile, model date, and score date for each CVE; stale or absent scores explicitly represented | P0 | In Progress | EPSS batch enrichment per CVE list | oss_scorer.py | OPG-029
OPG-031 | 3 | Registry metadata providers | Evidence Providers & Data Quality | PyPI and npm providers for versions, publish times, maintainers, deprecation, downloads, dist integrity | P0 | In Progress | 7-registry download-count system implemented | oss_scorer.py | OPG-023
OPG-032 | 3 | KEV and exploitation provider | Evidence Providers & Data Quality | Correlate CISA KEV by CVE; record catalog date, due date, ransomware flag, source | P0 | Done | KevProvider with TTL cache | src/osspolicyguard/kev.py | OPG-029
OPG-033 | 3 | Evidence conflict resolution | Evidence Providers & Data Quality | When providers disagree, preserve each assertion, rank authority/recency, show chosen value and rule, flag unresolved conflicts | P1 | Not Started |  | TBD | OPG-023
OPG-034 | 4 | Version-aware vulnerability matching | Vulnerability & Exploitability | Match advisories to exact resolved versions using ecosystem semantics; boundary, prerelease, epoch tests prevent false matches | P0 | Not Started |  | TBD | OPG-012,OPG-028
OPG-035 | 4 | Reachability evidence model | Vulnerability & Exploitability | Represent confirmed, likely, unknown, unreachable paths with method and evidence; unknown never becomes unreachable by default | P1 | Not Started |  | TBD | OPG-020
OPG-036 | 4 | VEX support | Vulnerability & Exploitability | Ingest CycloneDX and CSAF/OpenVEX statements, validate signer/issuer policy, respect expiry, retain justification | P1 | Not Started |  | TBD | OPG-028
OPG-037 | 4 | Exploitability-adjusted severity | Vulnerability & Exploitability | Compute documented risk contribution using CVSS, EPSS, KEV, reachability, exposure, criticality; each factor in explanation | P0 | Not Started |  | TBD | OPG-029,OPG-030,OPG-032
OPG-038 | 4 | Fix availability analysis | Vulnerability & Exploitability | Report first fixed version, safe upgrade candidates, breaking-change boundary, and no-fix status | P0 | Not Started |  | TBD | OPG-034
OPG-039 | 4 | Vulnerability aging | Vulnerability & Exploitability | Calculate time since publication, fix availability, policy SLA breach using injected clock; timezone and future-date tested | P1 | Not Started |  | TBD | OPG-034
OPG-040 | 4 | Advisory deduplication | Vulnerability & Exploitability | Merge CVE, GHSA, OSV, vendor aliases without losing source-specific severity, affected ranges, references, disagreement | P0 | Done | Union-find deduplication across all alias types | src/osspolicyguard/advisory_dedup.py | OPG-028
OPG-041 | 4 | Criticality-aware thresholds | Vulnerability & Exploitability | Application and component criticality profiles with explicit threshold differences; policy simulation demonstrates deterministic decisions | P0 | Not Started |  | TBD | OPG-056
OPG-042 | 4 | Compensating control input | Vulnerability & Exploitability | Signed, time-bounded attestations for isolation/mitigation; cannot suppress malicious-package blocks | P1 | Not Started |  | TBD | OPG-056
OPG-043 | 4 | Remediation ranking | Vulnerability & Exploitability | Rank upgrade, replace, isolate, patch, accept by risk reduction, compatibility cost, evidence confidence | P1 | Not Started |  | TBD | OPG-037,OPG-038
OPG-044 | 4 | Vulnerability result regression suite | Vulnerability & Exploitability | Curated fixtures for known vulnerable, fixed, disputed, withdrawn, prerelease, no-data cases | P0 | Not Started |  | TBD | OPG-034
OPG-045 | 5 | Malicious package feed aggregation | Supply Chain & Malicious Package Defense | Ingest at least two authoritative sources, preserve confidence and evidence, deduplicate aliases, fail closed under high-confidence rules | P0 | In Progress | OSV MAL- advisory integration + malicious-packages flag | oss_scorer.py | OPG-028
OPG-046 | 5 | Typosquatting similarity detection | Supply Chain & Malicious Package Defense | Detect edit-distance, homoglyph, separator, scope, common-prefix variants; benchmark precision/recall on labeled fixtures | P0 | Done | Levenshtein + homoglyph + separator detection, 120+ popular packages | src/osspolicyguard/typosquatting.py
OPG-047 | 5 | Dependency-confusion detection | Supply Chain & Malicious Package Defense | Flag public packages colliding with configured internal namespaces; require exact evidence and support allowlists | P0 | Done | Pattern-based internal namespace detection | src/osspolicyguard/dep_confusion.py
OPG-048 | 5 | Artifact integrity verification | Supply Chain & Malicious Package Defense | Verify registry integrity hashes and downloaded artifact digest; mismatch produces non-overridable block | P0 | Not Started |  | TBD | OPG-031
OPG-049 | 5 | Signed release verification | Supply Chain & Malicious Package Defense | Verify Sigstore attestations, identity constraints, transparency-log inclusion, artifact binding; distinguish absent from invalid | P1 | Not Started |  | TBD | OPG-095
OPG-050 | 5 | SLSA provenance assessment | Supply Chain & Malicious Package Defense | Validate provenance subject digest, builder identity, build type, source revision, policy level; report exact failed predicates | P1 | Not Started |  | TBD | OPG-095
OPG-051 | 5 | Release anomaly detection | Supply Chain & Malicious Package Defense | Detect unusual publisher, maintainer, release cadence, version jump, install-script, binary changes vs auditable baseline | P1 | Not Started |  | TBD | OPG-026
OPG-052 | 5 | Ownership-transfer risk | Supply Chain & Malicious Package Defense | Identify maintainer removals/additions and repo/package ownership transfer; weight by recency; require review for high-impact changes | P1 | Not Started |  | TBD | OPG-026
OPG-053 | 5 | Install-script and binary inventory | Supply Chain & Malicious Package Defense | List lifecycle scripts, native binaries, obfuscated payloads, network-capable code, newly introduced executables without executing | P0 | Done | npm .tgz and PyPI .whl analysis with size/path limits | src/osspolicyguard/artifact_inventory.py
OPG-054 | 5 | Package content diff | Supply Chain & Malicious Package Defense | Compare candidate and previously approved artifacts by file, permission, hash, script, dependency, binary changes | P1 | Not Started |  | TBD | OPG-053
OPG-055 | 5 | Quarantine workflow | Supply Chain & Malicious Package Defense | Store suspected artifacts and metadata in restricted location, prevent normal installation, assign case ID, analyst disposition | P1 | Not Started |  | TBD | OPG-045
OPG-056 | 6 | Versioned policy-as-code | Policy Engine & Explainability | Policy bundles declare schema, semver, effective date, owner, changelog; evaluation records exact policy digest | P0 | Done | PolicyBundle dataclass with SHA-256 digest | src/osspolicyguard/policy.py
OPG-057 | 6 | Deterministic evaluation | Policy Engine & Explainability | Identical normalized evidence, policy digest, tool version produce byte-stable decisions except documented timestamps | P0 | Not Started |  | TBD | OPG-056
OPG-058 | 6 | Three-state decision contract | Policy Engine & Explainability | APPROVED, REVIEW, PROHIBITED are mutually exclusive, derived from published rules; boundary tests cover every threshold | P0 | Done | Decision logic with threshold testing | oss_scorer.py | OPG-059
OPG-059 | 6 | Score direction and bounds | Policy Engine & Explainability | All dimensions and total score 0-100 where higher=safer; weights sum to 1.0, deductions capped, property tests prevent out-of-range | P0 | In Progress | Weights sum validation + gap fixes implemented | oss_scorer.py
OPG-060 | 6 | Missing-data semantics | Policy Engine & Explainability | Policy distinguishes pass, fail, unknown, unavailable, stale; missing evidence never silently zero or success | P0 | Done | DataPresence enum + apply_missing_data_rule() | src/osspolicyguard/policy.py
OPG-061 | 6 | Reason-coded findings | Policy Engine & Explainability | Each finding includes stable code, title, severity, dimension, evidence references, score effect, policy rule, remediation, confidence | P0 | Done | build_findings() with 8 typed finding rules | src/osspolicyguard/reports.py | OPG-062
OPG-062 | 6 | Decision trace | Policy Engine & Explainability | Machine-readable evaluation tree from raw evidence through normalized facts and rule outcomes to final decision | P0 | Not Started |  | TBD | OPG-061
OPG-063 | 6 | Policy unit-test framework | Policy Engine & Explainability | Organizations define positive/negative YAML test cases; policy test reports diffs and fails CI when decisions change | P1 | Not Started |  | TBD | OPG-056
OPG-064 | 6 | Policy simulation | Policy Engine & Explainability | Evaluate proposed policy against stored evidence without network calls; show decision changes and rule-level causes | P1 | Not Started |  | TBD | OPG-056
OPG-065 | 6 | Risk appetite profiles | Policy Engine & Explainability | Conservative, balanced, permissive examples differing through documented policy values only | P1 | Not Started |  | TBD | OPG-056
OPG-066 | 6 | False-positive feedback loop | Policy Engine & Explainability | Capture disputed finding, package/version, rule, evidence, disposition, reviewer, resolution time; never auto-weaken policy | P1 | Not Started |  | TBD | OPG-061
OPG-067 | 7 | CLI package scan | Outputs APIs & Developer Integrations | scan <package> supports text and JSON, validates inputs, documents exit codes, succeeds against offline fixtures | P0 | Done | Full CLI with text/json/sarif/markdown formats | src/osspolicyguard/cli.py
OPG-068 | 7 | CLI manifest scan | Outputs APIs & Developer Integrations | scan --manifest produces component and aggregate decisions, supports changed-only, bounded concurrency, deterministic ordering | P0 | Not Started | Stub implemented; full parsing pending | src/osspolicyguard/cli.py | OPG-015,OPG-017
OPG-069 | 7 | Versioned JSON report | Outputs APIs & Developer Integrations | Report validates against published schema, includes tool/policy versions, evidence freshness, findings, warnings; golden tests pass | P0 | Done | schema.json + JSON output format validated | schema.json / src/osspolicyguard/cli.py
OPG-070 | 7 | SARIF 2.1.0 output | Outputs APIs & Developer Integrations | Valid SARIF with stable rule IDs, package locations, severity mapping, help URIs, remediation; accepted by GitHub code scanning | P0 | Done | to_sarif() generating valid SARIF 2.1.0 | src/osspolicyguard/reports.py
OPG-071 | 7 | CycloneDX output enrichment | Outputs APIs & Developer Integrations | Add policy decision, risk, evidence references, vulnerability analysis as standards-compliant properties | P1 | Not Started |  | TBD | OPG-019
OPG-072 | 7 | Markdown pull-request report | Outputs APIs & Developer Integrations | Bounded summary with changed dependencies, blocks, review items, evidence freshness, remediation; long detail attached | P0 | Done | to_markdown_pr() with decision badge + evidence table | src/osspolicyguard/reports.py
OPG-073 | 7 | GitHub Action product | Outputs APIs & Developer Integrations | Versioned action with pinned runtime, inputs/outputs, least permissions, cache support, SARIF upload, decision gating | P0 | In Progress | Basic action workflow exists; not yet versioned | .github/workflows/
OPG-074 | 7 | Reusable CI templates | Outputs APIs & Developer Integrations | GitHub Actions, GitLab CI, Azure DevOps, Jenkins examples with secret handling and expected exit-code behavior | P1 | Not Started |  | TBD | OPG-073
OPG-075 | 7 | REST service | Outputs APIs & Developer Integrations | Optional service with authenticated scan, result, policy, health endpoints; OpenAPI schema, idempotency, quotas, async jobs | P2 | Not Started |  | TBD | OPG-007
OPG-076 | 7 | Webhook/event integration | Outputs APIs & Developer Integrations | Signed events for decision and exception lifecycle with replay protection, retry/backoff, delivery audit, stable payload | P2 | Not Started |  | TBD | OPG-075
OPG-077 | 7 | IDE/pre-commit integration | Outputs APIs & Developer Integrations | Fast changed-dependency checks with cached/offline evidence; reason codes and remediation visible before push | P1 | Not Started |  | TBD | OPG-025
OPG-078 | 8 | Approved component catalog | Enterprise Governance & Exceptions | Org-scoped approved package/version/digest records with policy, evidence snapshot, owner, approval date, review expiry | P1 | Not Started |  | TBD | OPG-081
OPG-079 | 8 | Exception workflow | Enterprise Governance & Exceptions | Exceptions require component scope, rule, justification, compensating control, requester, approver, expiry, ticket | P0 | Not Started |  | TBD | OPG-081
OPG-080 | 8 | Separation of duties | Enterprise Governance & Exceptions | Configurable roles prevent requesters from approving their own high-risk exceptions | P1 | Not Started |  | TBD | OPG-079
OPG-081 | 8 | Immutable audit log | Enterprise Governance & Exceptions | Record policy, decision, evidence digest, user/action, exception, config changes in append-only exportable records | P0 | Not Started |  | TBD | OPG-079
OPG-082 | 8 | Portfolio inventory | Enterprise Governance & Exceptions | Aggregate components across repositories preserving project and environment scope; exact version/digest queries | P1 | Not Started |  | TBD | OPG-078
OPG-083 | 8 | Continuous re-evaluation | Enterprise Governance & Exceptions | Re-evaluate approved components when advisory, exploit, ownership, release, or policy evidence changes | P1 | Not Started |  | TBD | OPG-078
OPG-084 | 8 | Policy inheritance | Enterprise Governance & Exceptions | Apply enterprise, business-unit, application, repository policies using explicit merge rules; protected controls not weakened downstream | P1 | Not Started |  | TBD | OPG-056
OPG-085 | 8 | Data retention controls | Enterprise Governance & Exceptions | Configure retention by evidence, report, audit, artifact type; legal hold overrides deletion; actions logged | P2 | Not Started |  | TBD | OPG-081
OPG-086 | 8 | Multi-tenant isolation | Enterprise Governance & Exceptions | Service-mode tenant data, caches, policies, tokens isolated; cross-tenant authorization and cache-key tests pass | P2 | Not Started |  | TBD | OPG-075
OPG-087 | 8 | SLA and ownership routing | Enterprise Governance & Exceptions | Route REVIEW/PROHIBITED findings by application owner and severity with due date, escalation, acknowledgment | P1 | Not Started |  | TBD | OPG-079
OPG-088 | 8 | Standards mapping | Enterprise Governance & Exceptions | Map controls to NIST SSDF, SLSA, OpenSSF Scorecard, OWASP SCVS with versioned non-overclaiming references | P1 | Not Started |  | TBD | OPG-056
OPG-089 | 9 | Threat model | Security Privacy & Reliability | Architecture/data-flow diagrams, assets, trust boundaries, threats, mitigations, residual risks for all operation modes | P0 | Not Started |  | TBD
OPG-090 | 9 | Secret management | Security Privacy & Reliability | Tokens only from approved env/secret providers; never in policy files; redacted from output; documented least scopes | P0 | Not Started |  | TBD | OPG-010
OPG-091 | 9 | Untrusted input hardening | Security Privacy & Reliability | Package names, manifests, archives, URLs, provider payloads have size/depth/time limits; traversal, zip bomb, SSRF tests pass | P0 | Not Started |  | TBD | OPG-093
OPG-092 | 9 | Network egress controls | Security Privacy & Reliability | Service mode supports provider allowlists, DNS/IP validation, proxy, TLS; blocks link-local/private unless configured | P0 | Not Started |  | TBD | OPG-075
OPG-093 | 9 | Safe artifact inspection | Security Privacy & Reliability | Never execute lifecycle scripts; archive parsing with CPU/memory/file-count/path/decompression limits in disposable workspace | P0 | Not Started |  | src/osspolicyguard/artifact_inventory.py | OPG-053
OPG-094 | 9 | Software bill of materials | Security Privacy & Reliability | Release pipeline generates CycloneDX SBOM for tool itself, signs it, attaches to releases, verifies dependency licenses | P0 | Not Started |  | TBD | OPG-149
OPG-095 | 9 | Hardened release provenance | Security Privacy & Reliability | Build releases in isolated CI with pinned actions, protected environment, artifact attestations, signed tags, checksums | P0 | Not Started |  | TBD | OPG-050
OPG-096 | 9 | Availability and graceful degradation | Security Privacy & Reliability | Provider outages produce partial/abstained results per policy; never false approval; timeout budget and outage matrix tests | P0 | Not Started |  | TBD | OPG-023
OPG-097 | 9 | Performance budgets | Security Privacy & Reliability | Document and test maximum memory, cold scan latency, cached scan latency, manifest throughput on fixed benchmark | P1 | Not Started |  | TBD | OPG-100
OPG-098 | 9 | Observability | Security Privacy & Reliability | Expose provider latency/error/cache metrics, evaluation counts, decision distribution without package names unless enabled | P1 | Not Started |  | TBD | OPG-010
OPG-099 | 9 | Backup and disaster recovery | Security Privacy & Reliability | Service data and policy stores have encrypted backups, tested restore, defined RPO/RTO, quarterly recovery evidence | P2 | Not Started |  | TBD | OPG-075
OPG-100 | 10 | Offline deterministic test suite | Quality Release & Documentation | Normal tests make no live network calls, use sanitized fixtures, run under supported Python versions, pass repeatedly | P0 | In Progress | 213 tests all fixture-based; no live API calls | tests/
OPG-101 | 10 | Coverage and mutation gates | Quality Release & Documentation | Enforce line/branch coverage on critical policy/provider modules and mutation-score threshold for decision logic | P1 | Not Started |  | TBD | OPG-100
OPG-102 | 10 | Static quality gates | Quality Release & Documentation | CI runs formatter check, lint, type check, dependency audit, secret scan, SAST, schema validation, tests; required checks block merge | P0 | In Progress | Basic CI workflow exists | .github/workflows/
OPG-103 | 10 | Provider contract fixtures | Quality Release & Documentation | Each provider has success, timeout, rate-limit, authentication, malformed, stale, empty, pagination, schema-change fixtures | P0 | In Progress | Fixture-based mocks in existing tests | tests/ | OPG-023
OPG-104 | 10 | End-to-end golden scenarios | Quality Release & Documentation | Golden tests cover safe, vulnerable, malicious, abandoned, ambiguous, stale-data, outage, exception, changed-dependency | P0 | Not Started |  | TBD | OPG-100
OPG-105 | 10 | Semantic versioning and changelog | Quality Release & Documentation | Automated release validates version, changelog, schema/policy compatibility, migration notes, signed artifacts, rollback | P0 | Not Started |  | TBD | OPG-095
OPG-106 | 10 | Public beta release gate | Quality Release & Documentation | Clean-room user installs, scans, interprets, enforces decision in under five minutes; all P0 requirements satisfied | P0 | Not Started |  | TBD | OPG-001
OPG-107 | 10 | Security policy and disclosure | Quality Release & Documentation | SECURITY.md states supported versions, private reporting path, response targets, disclosure process, safe-harbor | P0 | In Progress | SECURITY.md exists | SECURITY.md
OPG-108 | 10 | Operator documentation | Quality Release & Documentation | Document architecture, provider credentials, caching, rate limits, offline mode, policy rollout, exceptions, troubleshooting | P1 | Not Started |  | TBD | OPG-001
OPG-109 | 10 | Contributor governance | Quality Release & Documentation | CONTRIBUTING, code of conduct, DCO/CLA decision, issue/PR templates, maintainer roles, review rules, roadmap | P1 | Not Started |  | TBD
OPG-110 | 10 | Compatibility matrix | Quality Release & Documentation | Publish and test supported Python, OS, ecosystems, manifest versions, report schemas, action versions | P1 | Not Started |  | TBD | OPG-004
OPG-111 | 11 | Public benchmark methodology | Adoption Validation & Evidence | Labeled license-safe dataset and metrics for decision accuracy, false positives, coverage, provider failure, latency | P1 | Not Started |  | TBD | OPG-100
OPG-112 | 11 | Independent pilot program | Adoption Validation & Evidence | At least five pilots outside author's own projects; consented org context, workflow, findings, outcomes, reproducible evidence | P1 | Not Started |  | TBD
OPG-113 | 11 | Adoption telemetry without surveillance | Adoption Validation & Evidence | Opt-in aggregate scans, repeat usage, action references, downloads, versions; privacy notice; complete disablement supported | P1 | Not Started |  | TBD
OPG-114 | 11 | Impact evidence ledger | Adoption Validation & Evidence | Dated independent repositories, issues, PRs, citations, talks, pilots, findings, remediation; distinguish independent from self | P1 | Not Started |  | TBD
OPG-115 | 11 | Outcome validation | Adoption Validation & Evidence | For pilot findings, verify whether teams rejected, upgraded, replaced, isolated, or accepted components; quantify impact | P1 | Not Started |  | TBD | OPG-112
OPG-116 | 11 | External contributor pathway | Adoption Validation & Evidence | Label good-first issues, document setup, enforce review standards; report external contributors and merged changes | P1 | Not Started |  | TBD | OPG-109
OPG-117 | 11 | Independent technical review | Adoption Validation & Evidence | At least three qualified supply-chain security practitioners test defined scenarios and document methodology and findings | P1 | Not Started |  | TBD
OPG-118 | 11 | Academic evaluation package | Adoption Validation & Evidence | Citable release, DOI/archive, method paper, dataset card, reproducibility instructions, citation file | P2 | Not Started |  | TBD | OPG-111
OPG-119 | 11 | Upstream ecosystem contribution | Adoption Validation & Evidence | Contribute findings, rules, data-quality fixes to OpenSSF/OSV/Sigstore/SLSA or registries; retain accepted evidence | P1 | Not Started |  | TBD
OPG-120 | 11 | Case-study publication | Adoption Validation & Evidence | At least two consented independently verifiable case studies with baseline, intervention, outcome, third-party confirmation | P1 | Not Started |  | TBD | OPG-112
OPG-121 | 11 | Sustained-impact measurement | Adoption Validation & Evidence | Update adoption and outcome evidence quarterly for 12 months; preserve dated exports; explain discontinuities | P1 | Not Started |  | TBD | OPG-114
OPG-122 | 12 | Evidence-confidence fusion [Research] | Differentiation Research & IP Controls | Combine source authority, recency, independence, agreement, completeness into calibrated confidence with uncertainty | P1 | Not Started |  | TBD
OPG-123 | 12 | Temporal policy replay [Research] | Differentiation Research & IP Controls | Reconstruct decision at historical time using versioned evidence and policy; deterministic replay on public dataset | P1 | Not Started |  | TBD | OPG-056
OPG-124 | 12 | Counterfactual remediation optimizer [Research] | Differentiation Research & IP Controls | Compute smallest evidence-backed set of upgrades/replacements/controls/exceptions that changes a decision | P1 | Not Started |  | TBD | OPG-038,OPG-043
OPG-125 | 12 | Supply-chain change-point detection [Research] | Differentiation Research & IP Controls | Detect statistically significant shifts in release cadence, ownership, artifact composition; benchmark against labeled incidents | P1 | Not Started |  | TBD | OPG-051
OPG-126 | 12 | Blast-radius-aware policy [Research] | Differentiation Research & IP Controls | Combine dependency graph position, runtime reachability, deployment exposure, business criticality for org-specific impact | P1 | Not Started |  | TBD | OPG-020,OPG-035
OPG-127 | 12 | Adversarial package-campaign correlation [Research] | Differentiation Research & IP Controls | Cluster related suspicious packages by names, publishers, infrastructure, code/artifact similarity; explainable edges | P2 | Not Started |  | TBD | OPG-046
OPG-128 | 12 | Policy drift detector [Research] | Differentiation Research & IP Controls | Detect when provider/schema/scoring changes alter outcomes despite unchanged org intent; identify affected rules | P1 | Not Started |  | TBD | OPG-056
OPG-129 | 12 | Federated evidence sharing [Research] | Differentiation Research & IP Controls | Privacy-preserving exchange of verified package observations using signed minimal disclosures with revocation | P2 | Not Started |  | TBD | OPG-023
OPG-130 | 12 | Human-review learning safeguards [Research] | Differentiation Research & IP Controls | Use analyst outcomes to prioritize review without auto-changing enforcement; bias controls, holdout evaluation, rollback | P2 | Not Started |  | TBD | OPG-061
OPG-131 | 12 | Invention disclosure and prior-art gate | Differentiation Research & IP Controls | Document inventors, problem, mechanism, alternatives, experiments, dates, known prior art before public release of research features | P0 | Not Started |  | TBD
OPG-132 | 12 | Authorship and provenance archive | Differentiation Research & IP Controls | Preserve signed commits, design notebooks, dated experiments, releases, contributor attestations so authorship is auditable | P0 | Not Started |  | TBD
OPG-133 | 13 | SPDX license detection | License Compliance | Identify declared license from registry metadata and package files; parse SPDX expressions; store canonical SPDX identifier | P0 | Not Started |  | TBD | OPG-031
OPG-134 | 13 | Copyleft propagation analysis | License Compliance | Flag GPL-2/3, LGPL, AGPL, MPL, EPL; determine strong/weak copyleft applicability based on link type | P0 | Not Started |  | TBD | OPG-133
OPG-135 | 13 | License compatibility matrix | License Compliance | Configurable compatibility matrix; flag incompatible combinations in dependency graph; custom allow/deny rules | P1 | Not Started |  | TBD | OPG-133,OPG-134
OPG-136 | 13 | Dual-license and commercial restriction detection | License Compliance | Detect dual-licensed packages with commercial fees or non-commercial-use clauses; surface as REVIEW finding | P1 | Not Started |  | TBD | OPG-133
OPG-137 | 13 | License compliance report | License Compliance | Machine-readable report per component: license, compatibility verdict, applicable policy rule; JSON and Markdown outputs | P1 | Not Started |  | TBD | OPG-133,OPG-134,OPG-135
OPG-138 | 13 | Attribution / NOTICE file generation | License Compliance | Aggregate copyright notices and license texts for all direct and transitive dependencies; suitable for distribution bundles | P1 | Not Started |  | TBD | OPG-133,OPG-020
OPG-139 | 14 | Dependency pinning policy enforcement | Dependency Management Extended | Flag manifests with floating ranges (^, ~, *, latest, >x); configurable allowed range styles; lockfile hash-pin configurable | P0 | Not Started |  | TBD | OPG-015,OPG-017
OPG-140 | 14 | End-of-life and formal deprecation tracking | Dependency Management Extended | Ingest EOL dates from registry flags, endoflife.date API, language-runtime schedules; surface as REVIEW/PROHIBITED finding | P0 | Not Started |  | TBD | OPG-031
OPG-141 | 15 | Private registry provider | Evidence Providers Extended | JFrog Artifactory, Sonatype Nexus, GitHub Packages, AWS CodeArtifact, Azure Artifacts, GCP Artifact Registry support | P1 | Not Started |  | TBD | OPG-023
OPG-142 | 15 | Real-time new-version alerting | Evidence Providers Extended | Subscribe to registry feeds (npm hooks, PyPI RSS, crates.io); emit typed event when watched package risk score increases | P1 | Not Started |  | TBD | OPG-083
OPG-143 | 15 | Maintainer account credibility scoring | Evidence Providers Extended | Score account age, MFA status, prior release history, organisational affiliation; separate from ownership-transfer detection | P1 | Not Started |  | TBD | OPG-026,OPG-052
OPG-144 | 16 | Static behavioral analysis of package source | Supply Chain Defense Extended | AST-level analysis for outbound network calls, child-process spawning, filesystem writes, env-var exfiltration, dynamic eval | P0 | Not Started |  | TBD | OPG-053
OPG-145 | 16 | Phantom dependency detection | Supply Chain Defense Extended | Cross-reference static import analysis of user project source against declared manifest; identify phantom-satisfied imports | P1 | Not Started |  | TBD | OPG-020
OPG-146 | 16 | Source-artifact binding via reproducible-build equivalence | Supply Chain Defense Extended | Rebuild from declared source revision and compare digest to published artifact; report match, mismatch, or unverifiable | P1 | Not Started |  | TBD | OPG-049,OPG-050
OPG-147 | 16 | Adversarial namespace squatting detection | Supply Chain Defense Extended | Detect recently-registered packages (<30 days) closely matching popular package with no publisher history | P0 | Not Started |  | TBD | OPG-046,OPG-031
OPG-148 | 17 | Cross-ecosystem vulnerability cascade modeling [Research] | Policy Engine Extended | Model CVE propagation from C/C++ libraries to wrappers across npm/PyPI/Ruby/Maven; aggregate blast-radius with benchmark | P1 | Not Started |  | TBD | OPG-020,OPG-126
OPG-149 | 18 | SBOM generation for the analyzed project | Outputs & Integrations Extended | CycloneDX 1.5 or SPDX 2.3 SBOM of user's project enriched with policy decisions, CVSS, EPSS, license data | P0 | Not Started |  | TBD | OPG-019,OPG-133
OPG-150 | 18 | Automated fix pull-request creation | Outputs & Integrations Extended | When safe upgrade identified and token configured, open dependency-update PR modifying manifest and lock file | P1 | Not Started |  | TBD | OPG-038,OPG-073
OPG-151 | 18 | Container image and OS-package scanning | Outputs & Integrations Extended | Accept container image reference or OCI tarball; extract OS packages; scan through same policy engine | P1 | Not Started |  | TBD | OPG-023
OPG-152 | 18 | Package proxy / registry firewall mode | Outputs & Integrations Extended | Operate as HTTPS proxy in front of public registry; evaluate policy before package enters build environment | P1 | Not Started |  | TBD | OPG-075
OPG-153 | 19 | Compliance evidence packaging | Quality & Compliance Extended | SOC 2 Type II (CC7.2/CC8.1), FedRAMP, PCI-DSS SCA evidence bundles; JSON + Markdown; includes policy digest and remediation | P1 | Not Started |  | TBD | OPG-081,OPG-088
OPG-154 | 20 | LLM-assisted novel malicious pattern recognition [Research] | Research Extended | Language model explains suspicious behaviors not covered by rules; calibrated against confirmed-malicious corpus; no auto-enforcement | P2 | Not Started |  | TBD | OPG-053,OPG-144
OPG-155 | 20 | Runtime dependency inventory via instrumentation [Research] | Research Extended | Discover packages loaded in running Python/Node.js via import hooks or eBPF; compare to manifest; surface phantom deps | P2 | Not Started |  | TBD | OPG-145
OPG-156 | 20 | Infrastructure-as-Code deployment context enrichment [Research] | Research Extended | Parse Terraform, Helm, Kubernetes to determine deployment exposure; pass context to blast-radius model | P1 | Not Started |  | TBD | OPG-126,OPG-148
OPG-157 | 20 | Hierarchical team-scoped catalog with delegated administration | Research Extended | BU teams approve within enterprise envelope; application teams create scoped exceptions; revocation cascades | P1 | Not Started |  | TBD | OPG-078,OPG-084

## Workstream Summary
Workstream Summary
WS # | Name | Total | P0 | P1 | P2 | Done | In Progress | Not Started
1 | Architecture & Foundation
2 | Identity & Dependency Ingestion
3 | Evidence Providers & Data Quality
4 | Vulnerability & Exploitability
5 | Supply Chain & Malicious Package Defense
6 | Policy Engine & Explainability
7 | Outputs APIs & Developer Integrations
8 | Enterprise Governance & Exceptions
9 | Security Privacy & Reliability
10 | Quality Release & Documentation
11 | Adoption Validation & Evidence
12 | Differentiation Research & IP Controls
13 | License Compliance
14 | Dependency Management Extended
15 | Evidence Providers Extended
16 | Supply Chain Defense Extended
17 | Policy Engine Extended
18 | Outputs & Integrations Extended
19 | Quality & Compliance Extended
20 | Research Extended
TOTAL

## Roadmap
OSSPolicyGuard — Delivery Roadmap
Phase | Timeframe | Focus | Key Requirements | Success Criteria
Phase 1 — Foundation | Current | Core scanning engine and CLI | OPG-001–011, OPG-023–032, OPG-056–072 | All P0 foundation requirements done; 200+ tests
Phase 2 — Hardening | Q4 2025 | Security, compliance, quality | OPG-034–053, OPG-089–107 | Zero untrusted-input vulnerabilities; SARIF in GitHub Code Scanning
Phase 3 — Enterprise | Q1 2026 | Governance and integrations | OPG-073–088, OPG-133–153 | License compliance; SBOM output; exception workflow; audit log
Phase 4 — Scale | Q2 2026 | Adoption and pilots | OPG-111–121 | 5 independent pilots; benchmark published
Phase 5 — Research | Q3 2026 | Differentiation research | OPG-122–132, OPG-154–157 | 2+ research contributions submitted
Phases are indicative and subject to revision based on pilot feedback and resource availability.